{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["Project Tasks & Milestones","Example","Month Values"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":2,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Project Tasks & Milestones","index":0,"n_rows":140,"n_cols":13,"rows_kept":140,"cut":false,"hidden":false,"merged":[[0,14,0,19],[0,1,0,12],[1,1,7,12],[22,8,22,9],[23,8,23,9],[16,6,16,8],[20,1,20,12],[22,4,22,7],[23,4,23,7]],"flags":["formulas_cached_only"]}
[null,"INSTRUCTIONS"]
[null,"Fill in your lead organization, project name, control number, and proposed start date in the yellow highlighted boxes below the Instructions section.  Insert your project tasks and milestones into the table under the yellow boxes according to your project plan.  Organize Tasks, Subtasks, and Milestones to show their relationships and associations using numbers separated by periods in the \"Level\" columns as illustrated in the sample table below.  Designate the team member(s) responsible for accomplishment of each respective task or milestone in the \"Org(s) Responsible\" column.  If you wish to designate a milestone as Go/No-Go, enter a \"Y\" into the \"G/NG\" column next to the respective milestone.  Associate a starting and ending month with each task or milestone by selecting the appropriate month from the dropdown menu in the \"Start\" and \"End\" columns.  The \"Start Date\" and \"End Date\" columns will be automatically populated based upon your selections in the \"Start\" and \"End\" columns.  (Note that the auto-population function will not work if you do not enter a start date into the designated cell just above the table)  You may find it useful to determine your final targets/milestones for a particular task and then work backwards towards the start of the project, inserting appropriate intermediate tasks, subtasks, and milestones.  When crafting your Milestone Descriptions, think about how you will evaluate the success of the associated higher level task.  How can an objective observer decide that you were successful in achieving a task?  Be as quantitative and specific as possible, clearly indicating the techniques and assumptions used to determine their achievement.  See the \"Example\" tab for an illustration of the format and to get a sense for the level of detail requested.  Note that your last Task should be your Technology to Market (T2M) tasks and milestones."]
{"$rows_empty":7}
[null,"Level1","Level2","Level3","Org(s) Responsible","Title/Summary","Task Description","Milestone Description","G/NG (Y)","Start","End","Start Date","End Date"]
[{"$nulls":4},"Team organization(s) responsible for task/milestone accomplishement","Task name. Should be <10 words","Describe the <10 word task to the left in more detail.  This can be in as many words as you would like.","How will you evluate the success of the this task/subtask?  Make these as quantitative as possible.  (These will not have any text in the 2 columns to the left)",null,"Select from the dropdown menu","Select from the dropdown menu","This column will be auto populated","This column will be auto populated"]
[null,1,null,null,"Team Member 1","TASK 1: Brief Task Designation","Detailed Task Description",null,null,"Month 0","Month 12","2013-01-01","2014-01-01"]
[null,1,1.1,null,"Team Member 1","Subtask","Subtask Description",null,null,"Month 0","Month 6","2013-01-01","2013-07-01"]
[null,1,1.1,"1.1.1","Team Member 1",null,null,"Subtask Milestone",null,"Month 0","Month 6","2013-01-01","2013-07-01"]
[null,2,null,null,"Team Member 2","TASK 2: Brief Task Designation","Detailed Task Description",null,null,"Month 0","Month 24","2013-01-01","2015-01-01"]
[null,2,2.1,null,"Team Member 2",null,null,"Task Milestone","Y","Month 0","Month 6","2013-01-01","2013-07-01"]
[{"$nulls":6},"Cells in the above table are locked, fill in your project tasks and milestones in the table below"]
[]
[]
[]
[null,"PROJECT TASKS AND MILESTONES"]
[]
[null,null,null,"Lead Organization Name:","<< fill in organization >>",null,null,null,"Control Number:",null,"XXXX-XXXX"]
[null,null,null,"Project Name:","<< fill in project title >>",null,null,null,"Start Date: ",null,"MM/DD/YYYY"]
[]
[null,"Level1","Level2","Level3","Org(s) Responsible","Title/Summary","Task Description","Milestone Description","G/NG (Y)","Start","End","Start Date","End Date"]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]
[{"$nulls":11},{"$error":"#VALUE!"},{"$error":"#VALUE!"}]

{"sheet":"Example","index":1,"n_rows":40,"n_cols":13,"rows_kept":40,"cut":false,"hidden":false,"merged":[[1,8,1,9],[2,8,2,9],[1,4,1,7],[2,4,2,7]],"flags":["formulas_cached_only"]}
[]
[null,null,null,"Lead Organization Name:","Energy Inc",null,null,null,"Control Number:",null,"0123-4567"]
[null,null,null,"Project Name:","Make a Better Battery",null,null,null,"Start Date: ",null,"2013-01-01"]
[]
[null,"Level1","Level2","Level3","Org(s) Responsible","Title/Summary","Task Description","Milestone Description","G/NG (Y)","Start","End","Start Date","End Date"]
[null,1,null,null,"Energy Inc","TASK 1: Fabricate XYZ material with higher charge capacity","The goal of this task is to demonstrate that the novel XYZ material is capable of attaining a charge capacity of at least 4 mAh/cm2 at the 100 cm2 scale",null,null,"Month 0","Month 24","2013-01-01","2015-01-01"]
[null,1,1.1,null,"Energy Inc","Prepare XYZ material at the 10 cm2 scale","Demonstrate the ability to construct XYZ material with a high number of active sites per unit area and corresponding high charge capacity characteristics",null,null,"Month 0","Month 6","2013-01-01","2013-07-01"]
[null,1,1.1,"1.1.1","Energy Inc",null,null,"Demonstrate the ability to produce XYZ material with a microstructure corresponding to a 20-40 micron depth and 50-100 micron spacing (~2:1 aspect ratio) on a 10 cm2 sample with at most 2 defects per cm2",null,"Month 0","Month 3","2013-01-01","2013-04-01"]
[null,1,1.1,"1.1.2","Energy Inc",null,null,"Demonstrate the ability to produce XYZ material with 1:1 spacing:depth aspect ratio with at most 1 defect per cm2",null,"Month 3","Month 6","2013-04-01","2013-07-01"]
[null,1,1.1,"1.1.3","Energy Inc",null,null,"Demonstrate a 120 % increase in active sites in prepared XYZ material compared to ZYX material correlating to a 100% % increase in energy density",null,"Month 0","Month 6","2013-01-01","2013-07-01"]
[null,1,1.1,"1.1.4","Energy Inc",null,null,"Demonstrate production of a 10 cm2 area of XYZ material with at least 3 mAh/cm2 charge capacity with a max voltage of 5 V or greater at C/3 discharge rate for ≥ 100 cycles with <20% decrease in energy/charge capacity relative to initial values",null,"Month 3","Month 8","2013-04-01","2013-09-01"]
[null,1,1.1,"1.1.5","Energy Inc",null,null,"Demonstrate production of a 10 cm2 area of XYZ material with at least 5 mAh/cm2 charge capacity with a max voltage of 5 V or greater at C/3 discharge rate for ≥ 100 cycles with <20% decrease in energy/charge capacity relative to initial values",null,"Month 6","Month 12","2013-07-01","2014-01-01"]
[null,1,1.2,null,"Energy Inc","Prepare XYZ material at the 100 cm2 scale","Demonstrate the ability to construct XYZ material with the high surface area and charge capacity characteristics on a larger scale",null,null,"Month 9","Month 18","2013-10-01","2014-07-01"]
[null,1,1.2,"1.2.1","Energy Inc",null,null,"Demonstrate a 100 % increase in active sites in prepared XYZ material compared to ZYX material correlating to a 80% % increase in energy density",null,"Month 9","Month 14","2013-10-01","2014-03-01"]
[null,1,1.2,"1.2.2","Energy Inc",null,null,"Demonstrate production of a 100 cm2 area of XYZ material with at least 3 mAh/cm2 charge capacity with a max voltage of 5 V or greater at C/3 discharge rate for ≥ 80 cycles with <20% decrease in energy/charge capacity relative to initial values","Y","Month 9","Month 18","2013-10-01","2014-07-01"]
[null,1,1.2,"1.2.3","Energy Inc",null,null,"Demonstrate production of a 100 cm2 area of XYZ material with at least 4 mAh/cm2 charge capacity with a max voltage of 5 V or greater at C/3 discharge rate for ≥ 100 cycles with <20% decrease in energy/charge capacity relative to initial values",null,"Month 9","Month 18","2013-10-01","2014-07-01"]
[null,2,null,null,"National Lab","TASK 2: Integrate XYZ material into 3D battery architecture","The goal of this task is to incorporate the XYZ material developed into an optimized three dimensional structure to maximize energy density of the produced batteries",null,null,"Month 5","Month 12","2013-06-01","2014-01-01"]
[null,2,2.1,null,"National Lab",null,null,"Demonstrate a 3D battery structure with at least 50 J/kg energy density maintained for at least 60 charge/discharge cycles",null,"Month 5","Month 9","2013-06-01","2013-10-01"]
[null,2,2.2,null,"National Lab",null,null,"Demonstrate a 3D battery structure with at least 100 J/kg energy density maintained for at least 100 charge/discharge cycles",null,"Month 5","Month 12","2013-06-01","2014-01-01"]
[null,3,null,null,"Energy Inc, National Lab","TASK 3: XYZ material fabrication in a continuous process","The goal of this task is to continously produce XYZ material over areas greater than 2 m2 area with a 2 m/min production speed in a manner such that the material is uniform and retains mechanical stability",null,null,"Month 6","Month 24","2013-07-01","2015-01-01"]
[null,3,3.1,null,"Energy Inc, National Lab","Develop XYZ material roll-to-roll production process and equipment","Equipment will produce XYZ material continuously  while maintaining mechanical stablity and uniformity",null,null,"Month 6","Month 24","2013-07-01","2015-01-01"]
[null,3,3.1,"3.1.1","Energy Inc, National Lab",null,null,"Complete design schematic for a prototype roll-to-roll system with 2 m/min production speed; baseline process parameters established.",null,"Month 6","Month 9","2013-07-01","2013-10-01"]
[null,3,3.1,"3.1.2","Energy Inc, National Lab",null,null,"Complete construction of roll-to-roll prototype capable of producting 2 m/min of uniform, uncracked XYZ material with a total area greater than 2 m2","Y","Month 12","Month 18","2014-01-01","2014-07-01"]
[null,3,3.1,"3.1.3","Energy Inc, National Lab",null,null,"Demonstrated mechanical stability of material produced from the roll-to-roll process as measured by (insert stress test requirements)",null,"Month 12","Month 18","2014-01-01","2014-07-01"]
[null,3,3.1,"3.1.4","Energy Inc, National Lab",null,null,"Demonstrate an energy density of at least 100 J/kg for XYZ material produced by the roll-to-roll process",null,"Month 12","Month 18","2014-01-01","2014-07-01"]
[null,3,3.2,null,"Energy Inc, National Lab","Integrate XYZ material produced from the roll-to-roll process into a functional battery",null,null,null,"Month 18","Month 24","2014-07-01","2015-01-01"]
[null,3,3.2,"3.2.1","Energy Inc, National Lab",null,null,"Demonstrated ability of batteries created with XYZ material produced by the roll-to-roll printing equipment to exhibit an energy density of at least 50 J/kg for at least 70 charge-discharge cycles",null,"Month 18","Month 22","2014-07-01","2014-11-01"]
[null,3,3.2,"3.2.2","Energy Inc, National Lab",null,null,"Demonstrated ability of batteries created with XYZ material produced by the roll-to-roll printing equipment to exhibit an energy density of at least 100 J/kg for at least 100 charge-discharge cycles",null,"Month 18","Month 22","2014-07-01","2014-11-01"]
[null,4,null,null,"Energy Inc","Task 4: Technology to Market","The goal of this task is to develop a plan to transition the developed technology to the commercial market.  Technoeconomic and market analyses will be performed to present a convincing case to outside investors that deployment of the technology can sustainably generate a positive cash flow.   The team will actively enagage key stakeholders to transition the developed technology to industry towards the end of the project period.",null,null,"Month 0","Month 24","2013-01-01","2015-01-01"]
[null,4,4.1,null,"Energy Inc","Perform technoeconomic analyses of a commercially-relevant sized system","Technoeconomic analysis of a commercially-relevant sized system including sensitivity analysis determining factors most influential to the cost",null,null,"Month 0","Month 24","2013-01-01","2015-01-01"]
[null,4,4.1,"4.1.1","Energy Inc",null,null,"Preliminary analysis complete, detailing the most critical design components for a commercially-relevant system to approach the $100/kg target cost metric",null,"Month 0","Month 12","2013-01-01","2014-01-01"]
[null,4,4.1,"4.1.2","Energy Inc",null,null,"Final technoeconomic analysis delivered detailing the pathway towards economical larger scale production of the developed technology",null,"Month 12","Month 24","2014-01-01","2015-01-01"]
[null,4,4.2,null,"Energy Inc","Develop and revise (as needed) Technology to Market (T2M) plan",null,null,null,"Month 0","Month 24","2013-01-01","2015-01-01"]
[null,4,4.2,"4.2.1","Energy Inc",null,null,"Draft Technology to Market Plan submitted to ARPA-E",null,"Month 0","Month 3","2013-01-01","2013-04-01"]
[null,4,4.2,"4.2.2","Energy Inc",null,null,"ARPA-E approved complete Technology to Market Plan",null,"Month 0","Month 5","2013-01-01","2013-06-01"]
[null,4,4.2,"4.2.3","Energy Inc",null,null,"ARPA-E approved revision to Technology to Market plan (as needed)",null,"Month 6","Month 9","2013-07-01","2013-10-01"]
[null,4,4.2,"4.2.4","Energy Inc",null,null,"ARPA-E approved revision to Technology to Market plan (as needed)",null,"Month 9","Month 12","2013-10-01","2014-01-01"]
[null,4,4.2,"4.2.5","Energy Inc",null,null,"ARPA-E approved revision to Technology to Market plan (as needed)",null,"Month 12","Month 15","2014-01-01","2014-04-01"]
[null,4,4.2,"4.2.6","Energy Inc",null,null,"ARPA-E approved revision to Technology to Market plan (as needed)",null,"Month 15","Month 18","2014-04-01","2014-07-01"]
[null,4,4.2,"4.2.7","Energy Inc",null,null,"ARPA-E approved revision to Technology to Market plan (as needed)",null,"Month 18","Month 24","2014-07-01","2015-01-01"]

{"sheet":"Month Values","index":2,"n_rows":39,"n_cols":4,"rows_kept":39,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}
[]
[]
[null,null,"Month 0",0]
[null,null,"Month 1",1]
[null,null,"Month 2",2]
[null,null,"Month 3",3]
[null,null,"Month 4",4]
[null,null,"Month 5",5]
[null,null,"Month 6",6]
[null,null,"Month 7",7]
[null,null,"Month 8",8]
[null,null,"Month 9",9]
[null,null,"Month 10",10]
[null,null,"Month 11",11]
[null,null,"Month 12",12]
[null,null,"Month 13",13]
[null,null,"Month 14",14]
[null,null,"Month 15",15]
[null,null,"Month 16",16]
[null,null,"Month 17",17]
[null,null,"Month 18",18]
[null,null,"Month 19",19]
[null,null,"Month 20",20]
[null,null,"Month 21",21]
[null,null,"Month 22",22]
[null,null,"Month 23",23]
[null,null,"Month 24",24]
[null,null,"Month 25",25]
[null,null,"Month 26",26]
[null,null,"Month 27",27]
[null,null,"Month 28",28]
[null,null,"Month 29",29]
[null,null,"Month 30",30]
[null,null,"Month 31",31]
[null,null,"Month 32",32]
[null,null,"Month 33",33]
[null,null,"Month 34",34]
[null,null,"Month 35",35]
[null,null,"Month 36",36]